## Sheet1
Risk Register for Vietnamese Medicinal Plant Network
Prepared by: | DangNH |  |  | Date: | 16/02/2016
No | Risk | Description | Category | Root Cause | Triggers | Avoidance plan | Contigency plan | Fallback plan | Potential Responses | Risk Owner | Probability | Impact | Status
1 | Lack of team members |  | People | member out team | Dissatisfied with salary or other members, study abroad | PM need to have a meeting with this member and suggest him still be there. | resolve the problems. For example: salary increase | Hire other member |  | HoangLVQ | low | high
1 | Conflict among team members |  | People | Team member doesn't understand each others | Has issue inside team | Plan some team buildings to improve teammate | Have a meeting to resolve conflict problem | Switch member to other team. |  | HoangLVQ | medium | high
3 | Project is over budget |  | Financial | cost estimate is not exactly | out of budget | create a exactly cost management plan | cut costs | Incresae budget |  | HoangLVQ | high | medium
2 | Requirement is changed after project is started |  | Process | SRS not good (not realistic, not feasibility, not meet customer needs) | Customer (user) make change request. Or project team cannot develop the system as desciption in SRS. | Requirement should be paid a lot of attention. SRS should be reviewd carefully by PM and the supervisor. | With each requirement changes, the project tema should have a meeting to analysis the change requests and take actions. | Re-estimate and update plan. |  | ManhLN | high | medium
3 | Team member do not meet the deadline |  | Process | Undisciplined and habit of team member, loose management | Have a deadline | Setting rule and minus of do not meet the deadline: lost money and named at meeting minute. | Punish the member do not meet the deadline. Working over time. | Ask for help from out of team, supervisors. |  | KhanhKC | medium | medium
4 | Inability to verify/validate products against requirements. |  | Process |  | Inability to verify/validate products against requirements. | Print out the result to check by normal eyes. Debug into code to see how the code is running | Print out the result to check by normal eyes. Debug into code to see how the code is running | Ask for help from supervisors |  | NhungNTH | medium | low
5 | The server has defective parts. |  | Technology | Defective power supply… | Server is down… | Ensure the supplier provides with the adequate warranties. | Replace or fix the defective parts quickly. | Buy a new one. |  | HuyTDH | low | medium
6 | Delivery project doesn’t meet requirement |  | Process | Team member not understand requirement | Can't delivery project | Teamlead have to review sourcecode and follow requirement | Fix in next version | Extend dealine |  | HoangLVQ | medium | low
10
11
12
13