## Cover
TEST CASE
Project Name | Vietnamese Medicinal Plants Network |  |  | Creator | DangNHSE02992
Project Code | VMN |  |  | Reviewer/Approver | QuynhHTSE02639
Document Code | VMN_Integration Test Case_v1.0 |  |  | Issue Date | 2016-03-24
|  |  |  | Version | 1.0
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2016-03-24 | 1.0 |  | A | Add new | VMN_User Unit Test Case_v1.0_EN
Note on E11: *A: Add M: Modify D: Delete

## Test case List
TEST CASE LIST
Project Name |  | Vietnamese Medicinal Plants Network
Project Code |  | VMN
Test Environment Setup Description |  | List enviroment requires in this system 1. Server: Localhost 2. Database server: MySQL server 3. Browser: Google Chrome 40, Mozzila Firefox 30 4. Operation System: Mac OS X
No | Function Name | Sheet Name | Description | Pre-Condition
1 | User function | User_function | Integrating all functions of user together then execute test | Execute all Registered User unit test cases and passed
2 | Mod function | Mod_function | Integrating all functions of admin together then execute test | Execute all Mod unit test cases and passed
3 | Admin function | Admin_function | Integrating all functions of admin together then execute test | Execute all Admin unit test cases and passed

## Test Report
TEST REPORT
Project Name | Vietnamese Medicinal Plants Network |  | Creator |  | DangNHSE02992
Project Code | VMN |  | Reviewer/Approver |  | 24/03/2016
Document Code | VMN_Integration Test Report_v1.0 |  | Issue Date
Notes
No | Module code | Pass | Fail | Untested | N/A | Number of test cases
1 | User_Function | 76 | 0 | 0 | 0 | 76
2 | Mod_Function | 44 | 0 | 0 | 0 | 44
3 | Admin_Function | 22 | 0 | 0 | 0 | 22
| Sub total | 142 | 0 | 0 | 0 | 142
| Test coverage |  | 100 | %
| Test successful coverage |  | 100 | %

## User Module
Back to Test Report
Module Code | User Module | [5 empty] | Pass |  | Pass
Test requirement | This test cases were created to test integration between login with all functions and all functions together | [5 empty] | Fail |  | Fail
Tester | DangNHSE02992 | [5 empty] | N/A
Pass | Fail | Untested | N/A | Number of Test cases |  |  | Untested |  | Untesed
76 | 0 | 0 | 0 | 76 |  |  |  |  | N/A
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Result Chorme version 40 | Result Firefox version 30 | Test date | Note
Integration Login with Logout
[User Module-2] | Check "Logout" hyperlink | 1. Login VMN system by Member or Mod role. | 1. Homepage is displayed with "Logout" hyperlink on Header |  | Pass | Pass | 23/3/2016
[User Module-3] | When user click on "Logout" hyperlink | 1. Login VMN system by Member or Mod role. 2. Click on "Logout" hyperlink on Header | 1. Homepage is displayed 2. Logout success and redirect to Homepage |  | Pass | Pass | 23/3/2016
Integration Register with Login
[User Module-5] | When user register new account | 1. Go to vmn.vnvalley.com 2. Click on "Register" hyperlink in Header 3. Enter personal information in "Register" Form 4. Click on "Sign up" button | 1.Homepage is displayed 2. "Register" Page is displayed 3. Display user's information correctly 4. VMN system will alert message:"Register success." and redirect to "Login" Page | [Authentication-18] [Authentication-2] | Pass | Pass | 23/3/2016
[User Module-6] | When user register new account | 1. Go to vmn.vnvalley.com 2. Click on "Login" hyperlink in Header 3. Click on "Register" hyperlink in "Login" Page 4. Enter personal information in "Register" Form 5. Click on "Sign up" button | 1.Homepage is displayed 2. "Login" Page is displayed 3. "Register" Page is displayed 4. Display user's information correctly 5. VMN system will alert message:"Register success." and redirect to "Login" Page |  | Pass | Pass | 23/3/2016
Integration Login with Personal Page
[User Module-8] | Check "Personal Name" hyperlink | 1. Login VMN system by Member or Mod role. | 1. Homepage is displayed with "Personal Name" hyperlink on Header |  | Pass | Pass | 23/3/2016
[User Module-9] | "Personal Name" hyperlink when user click on | 1. Login VMN system by Member or Mod role. 2. Click on "Personal Page" hyperlink on Header | 1. Homepage is displayed 2. "Personal Page" Page is displayed | [Personal Page-2] | Pass | Pass | 23/3/2016
Integration Slider on Homepage with Medicinal Plants tab
[User Module-11] | Check "View now" in Medicinal Plants Slider on Homepage | 1. Go to vmn.vnvalley.com 2. Click on "View now" in Medicinal Plants Slider (Slider 2) | 1. Homepage is displayed 2. "Medicinal Plants" tab is displayed | [Homepage-8] | Pass | Pass | 23/3/2016
Integration Slider on Homepage with Remedy tab
[User Module-13] | Check "View now" in Remedy Slider on Homepage | 1. Go to vmn.vnvalley.com 2. Click on "View now" in Remedy Slider (Slider 3) | 1. Homepage is displayed 2. "Remedy" tab is displayed | [Homepage-10] | Pass | Pass | 23/3/2016
Integration Slider on Homepage with HMS tab
[User Module-15] | Check "View now" in HMS Slider on Homepage | 1. Login VMN system by Member or Mod role. 2. Click on "View now" in HMS Slider (Slider 4) | 1. Homepage is displayed 2. "HMS Search" Page is displayed | [Herbal Medicine Store-2] | Pass | Pass | 23/3/2016
Integration Login with Medicinal plants
[User Module-17] | Check "Medicinal plants" tab | 1. Login VMN system by Member or Mod role 2. Click on "Medicinal plants" on Header | 1. Homepage is displayed 2. "Medicinal plants" Page is displayed | [Homepage-9] | Pass | Pass | 23/3/2016
Integration Login with Remedy
[User Module-19] | Check "Remedy" tab | 1. Login VMN system by Member or Mod role 2. Click on "Remedy" on Header | 1. Homepage is displayed 2. "Remedy" Page is displayed | [Homepage-11] | Pass | Pass | 23/3/2016
Integration Login with Herbal Medicine Store
[User Module-21] | Check "HMS" tab | 1. Login VMN system by Member or Mod role 2. Click on "HMS" tab on Header | 1. Homepage is displayed 2. "HMS Searching" Page is displayed | [Herbal Medicine Store-6] | Pass | Pass | 23/3/2016
Integration Personal page with "Medicinal Plants change content" Page
[User Module-23] | Check "Medicinal Plants" hyperlink on "Contributed Articles" in "Personal Page" Page | 1. Login VMN system by Member role 2. Click on "Account" hyperlink on Header 3. Click on "Contributed Articles" tab 4. Click on "Medicinal Plants Name" hyperlink | 1. Homepage is displayed 2. "Personal Page" Page is displayed 3. "Contributed Article" Frame is displayed 4. "Medicinal Plants change content" Page is displayed | [Medicinal Plants Article-23] | Pass | Pass | 23/3/2016
Integration Personal Page with "Remedy's change content" Page
[User Module-25] | Check "Remedy" hyperlink on "Contributed Articles" in "Personal Page" Page | 1. Login VMN system by Member role 2. Click on "Account" hyperlink on Header 3. Click on "Contributed Articles" tab 4. Click on "Remedy Article's Title" hyperlink | 1. Homepage is displayed 2. "Personal Page" Page is displayed 3. "Contributed Article" Frame is displayed 4. "Remedy change content" Page is displayed | [Remedy Article-21] | Pass | Pass | 23/3/2016
Integration Medicinal plants with Remedy
[User Module-27] | Check "Related Remedy Article" hyperlink | 1. Go to vmn.vnvalley.com 2. Click on "Medicinal Plants" on Header 3. Click on "Detail" hyperlink of any Medicinal Plants Article 4. Click on "Related Remedy Article" tab 5. Click on any "Remedy Article" hyperlink | 1. Homepage is displayed 2. "Medicinal Plants" tab is displayed 3. "Medicinal Plants Article Detail" Page is displayed 4. "Related Remedy Article" tab is displayed by list of Remedy Article hyperlink 5. "Remedy Article Detail" is displayed | [Remedy Article-37] | Pass | Pass | 23/3/2016
Integration Medicinal plants with Personal Page
[User Module-29] | Check "Author" hyperlink | 1. Go to vmn.vnvalley.com 2. Click on "Medicinal Plants Article Detail" hyperlink on "Medicinal Plants" tab or Homepage 3. Click on "Author" hyperlink | 1. Homepage is displayed 2. "Medicinal Plants Article Detail" Page is displayed 3. "Author" Page is displayed by following fields: - Header - Avatar - Profile hyperlink - Contributed Articles hyperlink - Profile frame - Footer |  | Pass | Pass | 23/3/2016
Integration Remedy with HMS
[User Module-31] | Check "Related HMS" hyperlink | 1. Login VMN system by Member or Mod role 2. Click on "Remedy Article Detail" hyperlink on "Remedy" tab 3. Click on "Related HMS" tab 4. Click on "HMS" hyperlink | 1. Homepage is displayed 2. "Remedy Article Detail" Page is displayed 3. "Related HMS" tab is displayed by list of HMS hyperlink 4. "HMS Profile" Page is displayed | [Herbal Medicine Store-13] | Pass | Pass | 23/3/2016
Integration Remedy with Personal Page
[User Module-33] | Check "Author" hyperlink | 1. Go to vmn.vnvalley.com 2. Click on "Remedy Article Detail" hyperlink on "Remedy" tab 3. Click on "Author" hyperlink | 1. Homepage is displayed 2. "Remedy Article Detail" Page is displayed 3. "Author" Page is displayed by following fields: - Header - Avatar - Profile hyperlink - Contributed Articles hyperlink - Profile frame - Footer |  | Pass | Pass | 23/3/2016
Integration Advance Search with Medicinal Plants Detail
[User Module-35] | Check "Medicinal Plants Article" hyperlink | 1. Log in VMN system by Member role 2. Click on "Medicinal Plants" tab 3. Click on "Advance Search" button 4. Enter searching information then click "Search" button 5. Click on "Medicinal Plants Article" hyperlink | 1. Homepage is displayed 2. "Medicinal Plants" tab is displayed 3. "Advance Search" Page is displayed 4. Search result is displayed in "Searching Result" Frame 5. "Medicinal Plants Article Detail" Page is displayed | [Medicinal Plants Article- 62] | Pass | Pass | 23/3/2016
Integration Advance Search with Remedy Detail
[User Module-37] | Check "Remedy Article" hyperlink | 1. Log in VMN system by Member role 2. Click on "Remedy" tab 3. Click on "Advance Search" button 4. Enter searching information then click "Search" button 5. Click on "Remedy Article" hyperlink | 1. Homepage is displayed 2. "Remedy" tab is displayed 3. "Advance Search" Page is displayed 4. Search result is displayed in "Searching Result" Frame 5. "Remedy Article Detail" Page is displayed | [Remedy Article- 60] | Pass | Pass | 23/3/2016
Security
Check copy & paste link to other browser
ID-22 | Homepage | 1. Login on one browser 2. Copy link 3. Change to other browser 4. Paste link and press Enter | Login screen is displayed. |  | Pass | Pass | 24/3/2016
ID-23 | Medicinal Plant | 1. Login on one browser 2. Click "Mecicinal plant" menu 3. Copy link 4. Change to other browser 5. Paste link and press Enter | Login screen is displayed. |  | Pass | Pass | 24/3/2016
ID-24 | Remedy | 1. Login on one browser 2. Click "Remedy" menu 3. Copy link 4. Change to other browser 5. Paste link and press Enter | Login screen is displayed. |  | Pass | Pass | 24/3/2016
ID-25 | Herb Store Medicine | 1. Login on one browser 2. Click "HMS" menu 3. Copy link 4. Change to other browser 5. Paste link and press Enter | Login screen is displayed. |  | Pass | Pass | 24/3/2016
ID-26 | Personal Page | 1. Login on one browser 2. Click Message 3. Copy link 4. Change to other browser 5. Paste link and press Enter | Login screen is displayed. |  | Pass | Pass | 24/3/2016
UI
ID-27 | Check displaying default language of the system when open website | 1. Set language of Browser isVietnamese 2. Start system from browser 3. Confirm displaying language of system | Language of system is Vietnamese |  | Pass | Pass | 24/3/2016
ID-28 | Check width of browser < 800x600 px | Check width of page | - Width of page is 800x600 - Scrollbar of browser is displayed |  | Pass | Pass | 24/3/2016
ID-29 | Check width of browser ≥ 800x600 px | Check width of page | - Width of page is equal to width of browser - Scrollbar of browser is not displayed |  | Pass | Pass | 24/3/2016
ID-30 | Check display greeting when user login successfully | 1. Login successfully 2. Confirm display greeting | Display Homepage with name and avatar of user |  | Pass | Pass | 24/3/2016
ID-31 | Check header of screen | Confirm header of screen | Display header that has font, layout & spelling is the same as design |  | Pass | Pass | 24/3/2016
ID-32 | Check footer of screen | Confirm footer of screen | Display footer that has font, layout & spelling is the same as design: |  | Pass | Pass | 24/3/2016
ID-33 | Check title of screen | Confirm title of screen | Display title that has font, layout & spelling is the same as design |  | Pass | Pass | 24/3/2016
ID-34 | Check GUI of link | Check UI of link | Display link that has font, layout & spelling is the same as design |  | Pass | Pass | 24/3/2016
ID-35 | Check GUI of menu on screen | Confirm label on menu | Display label that has font, layout & spelling is the same design |  | Pass | Pass | 24/3/2016
ID-36 | Check tab order | Press tab continuously | Tab order follow: left to right, top to down |  | Pass | Pass | 24/3/2016
ID-37 | Check mouse hover | Mouse hover over link | Mouse pointer has hand symbol |  | Pass | Pass | 24/3/2016
ID-38 | Check tab selection color | Confirm tab selection color | Color of selected tab is changed |  | Pass | Pass | 24/3/2016
ID-39 | Check consistent color of tab selection on all pages | Confirm consistent color of tab selection on all pages | Color of all tabs selection is the same |  | Pass | Pass | 24/3/2016
Note on F10: Pass Fail Untested N/A
Note on G10: Pass Fail Untested N/A

## Mod Module
Back to Check Report
Module Code | Mod_login | [7 empty] | Pass
Check requirement | This Check cases were created to Check integration between login with all functions and all functions together | [7 empty] | Fail
Checker | DangNHSE02992
Pass | Fail | UnChecked | N/A | Number of Check cases |  |  |  |  | Untesed
44 | 0 | 0 | 0 | 44 |  |  |  |  | N/A
ID | Check Case Description | Check Case Procedure | Expected Output | Inter-Check case Dependence | Result Chorme version 40 | Result Firefox version 30 | Check date | Note
Integration Login with Logout
[Mod_login-2] | When Mod click on "Logout" hyperlink | 1. Login VMN system by Mod role 2. Click on "Logout" hyperlink on Header | 1. Mod Page is displayed 2. Log out success and redirect to "Login" Page | [Mod Module- 18] | Pass | Pass | 22/3/2016
Integration Login with Dashboard
[Mod_login-4] | Check "Dashboard" Page | 1. Login VMN system by Mod role 2. Click on "Dashboard" hyperlink | 1. Mod Page is displayed 2. "Dashboard" Page is displayed | [Mod Module- 20] | Pass | Pass | 22/3/2016
Integration Login with Medicinal Plants Article Management
[Mod_login-6] | Check "Medicinal Plants Article Management" Page | 1. Login VMN system by Mod role 2. Click on "Medicinal Plants Article Management" hyperlink | 1. Mod Page is displayed 2. "Medicinal Plants Article Management" Page is displayed | [Mod Module- 36] | Pass | Pass | 22/3/2016
Integration Login with Remedy Article Management
[Mod_login-8] | Check "Remedy Article Management" Page | 1. Login VMN system by Mod role 2. Click on "Remedy Article Management" hyperlink | 1. Mod Page is displayed 2. "Remedy Article Management" Page is displayed | [Mod Module- 50] | Pass | Pass | 22/3/2016
Integration Medicinal Plants Articles Management with Medicinal Plants Article Detail
[Mod_login-10] | When Mod click on "Detail" button on "Medicinal Plants Article Pending" tab of "Medicinal Plants Article Management" Page | 1. Login VMN system by Mod role 2. Click on "Medicinal Plants Article Management" hyperlink 3. Click on "Detail" button of any article on "Medicinal Plants Article Pending" tab | 1. Mod Page is displayed 2. "Medicinal Plants Article Management" Page is displayed 3. "Medicinal Plants Article Detail" Page is displayed | [Mod Module- 40] | Pass | Pass | 22/3/2016
[Mod_login-11] | When Mod click on "Accept" button on "Medicinal Plants Article Detail" Page | 1. Login VMN system by Mod role 2. Click on "Medicinal Plants Article Management" hyperlink 3. Click on "Detail" button of any article on "Pending Medicinal Plants Article" tab 4. Click on "Accept" button on "Medicinal Plants Article Detail" Page | 1. Mod Page is displayed 2. "Medicinal Plants Article Management" Page is displayed 3. "Medicinal Plants Article Detail" Page is displayed 4. "Medicinal Plants Article Management" Page is displayed | [Mod Module- 41] | Pass | Pass | 22/3/2016
[Mod_login-12] | When Mod click on "Deny" button on "Medicinal Plants Article Detail" Page | 1. Login VMN system by Mod role 2. Click on "Medicinal Plants Article Management" hyperlink 3. Click on "Detail" button of any article on "Pending Medicinal Plants Article" tab 4. Click on "Deny" button on "Medicinal Plants Article Detail" Page | 1. Mod Page is displayed 2. "Medicinal Plants Article Management" Page is displayed 3. "Medicinal Plants Article Detail" Page is displayed 4. "Medicinal Plants Article Management" Page is displayed | [Mod Module- 42] | Pass | Pass | 22/3/2016
[Mod_login-13] | When Mod click on "Detail" button on "Change content's Medicinal Plants Article" tab of "Medicinal Plants Article Management" Page | 1. Login VMN system by Mod role 2. Click on "Medicinal Plants Article Management" hyperlink 3. Click on "Change content's Medicinal Plants Article" tab 4. Click on "Detail" button of any article on "Change content's Medicinal Plants Article" tab | 1. Mod Page is displayed 2. "Medicinal Plants Article Management" Page is displayed 3. "Change content's Medicinal Plants Article" tab is displayed 4. "Medicinal Plants Article Management" Page is displayed | [Mod Module- 43] | Pass | Pass | 22/3/2016
[Mod_login-14] | When Mod click on "Accept" button on "Medicinal Plants Article Detail" Page | 1. Login VMN system by Mod role 2. Click on "Medicinal Plants Article Management" hyperlink 3. Click on "Change content's Medicinal Plants Article" tab 4. Click on "Detail" button of any article on "Change content's Medicinal Plants Article" tab 5. Click on "Accept" button on "Medicinal Plants Article Detail" Page | 1. Mod Page is displayed 2. "Medicinal Plants Article Management" Page is displayed 3. "Change content's Medicinal Plants Article" tab is displayed 4. "Medicinal Plants Article Detail" Page is displayed 5. "Change content's Medicinal Plants Article" tab is displayed | [Mod Module- 44] | Pass | Pass | 22/3/2016
[Mod_login-15] | When Mod click on "Deny" button on "Medicinal Plants Article Detail" Page | 1. Login VMN system by Mod role 2. Click on "Medicinal Plants Article Management" hyperlink 3. Click on "Change content's Medicinal Plants Article" tab 4. Click on "Detail" button of any article on "Change content's Medicinal Plants Article" tab 5. Click on "Deny" button on "Medicinal Plants Article Detail" Page | 1. Mod Page is displayed 2. "Medicinal Plants Article Management" Page is displayed 3. "Change content's Medicinal Plants Article" tab is displayed 4. "Medicinal Plants Article Detail" Page is displayed 5. "Change content's Medicinal Plants Article" tab is displayed | [Mod Module- 45] | Pass | Pass | 22/3/2016
[Mod_login-16] | When Mod click on "Detail" button on "Reported Medicinal Plants Article" tab of "Medicinal Plants Article Management" Page | 1. Login VMN system by Mod role 2. Click on "Medicinal Plants Article Management" hyperlink 3. Click on "Reported Medicinal Plants Article" tab 4. Click on "Detail" button of any article on "Reported Medicinal Plants Article" tab | 1. Mod Page is displayed 2. "Medicinal Plants Article Management" Page is displayed 3. "Medicinal Plants Article Detail" Page is displayed 4. "Medicinal Plants Article Management" Page is displayed | [Mod Module- 46] | Pass | Pass | 22/3/2016
[Mod_login-17] | When Mod click on "Accept" button on "Medicinal Plants Article Detail" Page | 1. Login VMN system by Mod role 2. Click on "Medicinal Plants Article Management" hyperlink 3. Click on "Reported Medicinal Plants Article" tab 4. Click on "Detail" button of any article on "Reported Medicinal Plants Article" tab 5. Click on "Accept" button on "Medicinal Plants Article Detail" Page | 1. Mod Page is displayed 2. "Medicinal Plants Article Management" Page is displayed 3. "Reported Medicinal Plants Article" tab is displayed 4. "Medicinal Plants Article Detail" Page is displayed 5. "Reported Medicinal Plants Article" tab is displayed | [Mod Module- 47] | Pass | Pass | 22/3/2016
[Mod_login-18] | When Mod click on "Deny" button on "Medicinal Plants Article Detail" Page | 1. Login VMN system by Mod role 2. Click on "Medicinal Plants Article Management" hyperlink 3. Click on "Reported Medicinal Plants Article" tab 4. Click on "Detail" button of any article on "Reported Medicinal Plants Article" tab 5. Click on "Deny" button on "Medicinal Plants Article Detail" Page | 1. Mod Page is displayed 2. "Medicinal Plants Article Management" Page is displayed 3. "Reported Medicinal Plants Article" tab is displayed 4. "Medicinal Plants Article Detail" Page is displayed 5. "Reported Medicinal Plants Article" tab is displayed | [Mod Module- 48] | Pass | Pass | 22/3/2016
Integration Remedy Articles Management with Remedy Article Detail
[Mod_login-20] | When Mod click on "Detail" button on "Remedy Article Pending" tab of "Remedy Article Management" Page | 1. Login VMN system by Mod role 2. Click on "Remedy Article Management" hyperlink 3. Click on "Detail" button of any article on "Remedy Article Pending" tab | 1. Mod Page is displayed 2. "Remedy Article Management" Page is displayed 3. "Remedy Article Detail" Page is displayed | [Mod Module- 54] | Pass | Pass | 22/3/2016
[Mod_login-21] | When Mod click on "Accept" button on "Remedy Article Detail" Page | 1. Login VMN system by Mod role 2. Click on "Remedy Article Management" hyperlink 3. Click on "Detail" button of any article on "Pending Remedy Article" tab 4. Click on "Accept" button on "Remedy Article Detail" Page | 1. Mod Page is displayed 2. "Remedy Article Management" Page is displayed 3. "Remedy Article Detail" Page is displayed 4. "Remedy Article Management" Page is displayed | [Mod Module- 55] | Pass | Pass | 22/3/2016
[Mod_login-22] | When Mod click on "Deny" button on "Remedy Article Detail" Page | 1. Login VMN system by Mod role 2. Click on "Remedy Article Management" hyperlink 3. Click on "Detail" button of any article on "Pending Remedy Article" tab 4. Click on "Deny" button on "Remedy Article Detail" Page | 1. Mod Page is displayed 2. "Remedy Article Management" Page is displayed 3. "Remedy Article Detail" Page is displayed 4. "Remedy Article Management" Page is displayed | [Mod Module- 56] | Pass | Pass | 22/3/2016
[Mod_login-23] | When Mod click on "Detail" button on "Change content's Remedy Article" tab of "Remedy Article Management" Page | 1. Login VMN system by Mod role 2. Click on "Remedy Article Management" hyperlink 3. Click on "Change content's Remedy Article" tab 4. Click on "Detail" button of any article on "Change content's Remedy Article" tab | 1. Mod Page is displayed 2. "Remedy Article Management" Page is displayed 3. "Change content's Remedy Article" tab is displayed 4. "Remedy Article Management" Page is displayed | [Mod Module- 57] | Pass | Pass | 22/3/2016
[Mod_login-24] | When Mod click on "Accept" button on "Remedy Article Detail" Page | 1. Login VMN system by Mod role 2. Click on "Remedy Article Management" hyperlink 3. Click on "Change content's Remedy Article" tab 4. Click on "Detail" button of any article on "Change content's Remedy Article" tab 5. Click on "Accept" button on "Remedy Article Detail" Page | 1. Mod Page is displayed 2. "Remedy Article Management" Page is displayed 3. "Change content's Remedy Article" tab is displayed 4. "Remedy Article Detail" Page is displayed 5. "Change content's Remedy Article" tab is displayed | [Mod Module- 58] | Pass | Pass | 22/3/2016
[Mod_login-25] | When Mod click on "Deny" button on "Remedy Article Detail" Page | 1. Login VMN system by Mod role 2. Click on "Remedy Article Management" hyperlink 3. Click on "Change content's Remedy Article" tab 4. Click on "Detail" button of any article on "Change content's Remedy Article" tab 5. Click on "Deny" button on "Remedy Article Detail" Page | 1. Mod Page is displayed 2. "Remedy Article Management" Page is displayed 3. "Change content's Remedy Article" tab is displayed 4. "Remedy Article Detail" Page is displayed 5. "Change content's Remedy Article" tab is displayed | [Mod Module- 59] | Pass | Pass | 22/3/2016
[Mod_login-26] | When Mod click on "Detail" button on "Reported Remedy Article" tab of "Remedy Article Management" Page | 1. Login VMN system by Mod role 2. Click on "Remedy Article Management" hyperlink 3. Click on "Reported Remedy Article" tab 4. Click on "Detail" button of any article on "Reported Remedy Article" tab | 1. Mod Page is displayed 2. "Remedy Article Management" Page is displayed 3. "Remedy Article Detail" Page is displayed 4. "Remedy Article Management" Page is displayed | [Mod Module- 60] | Pass | Pass | 22/3/2016
[Mod_login-27] | When Mod click on "Accept" button on "Remedy Article Detail" Page | 1. Login VMN system by Mod role 2. Click on "Remedy Article Management" hyperlink 3. Click on "Reported Remedy Article" tab 4. Click on "Detail" button of any article on "Reported Remedy Article" tab 5. Click on "Accept" button on "Remedy Article Detail" Page | 1. Mod Page is displayed 2. "Remedy Article Management" Page is displayed 3. "Reported Remedy Article" tab is displayed 4. "Remedy Article Detail" Page is displayed 5. "Reported Remedy Article" tab is displayed | [Mod Module- 61] | Pass | Pass | 22/3/2016
[Mod_login-28] | When Mod click on "Deny" button on "Remedy Article Detail" Page | 1. Login VMN system by Mod role 2. Click on "Remedy Article Management" hyperlink 3. Click on "Reported Remedy Article" tab 4. Click on "Detail" button of any article on "Reported Remedy Article" tab 5. Click on "Deny" button on "Remedy Article Detail" Page | 1. Mod Page is displayed 2. "Remedy Article Management" Page is displayed 3. "Reported Remedy Article" tab is displayed 4. "Remedy Article Detail" Page is displayed 5. "Reported Remedy Article" tab is displayed | [Mod Module- 62] | Pass | Pass | 22/3/2016
Note on F10: Pass Fail Untested N/A
Note on G10: Pass Fail Untested N/A

## Admin Module
Back to Check Report
Module Code | Admin_login | [7 empty] | Pass
Check requirement | This Check cases were created to Check integration between login with all functions and all functions together | [7 empty] | Fail
Checker | DangNHSE02992
Pass | Fail | UnChecked | N/A | Number of Check cases |  |  |  |  | Untesed
22 | 0 | 0 | 0 | 22 |  |  |  |  | N/A
ID | Check Case Description | Check Case Procedure | Expected Output | Inter-Check case Dependence | Result Chorme version 40 | Result Firefox version 30 | Check date | Note
Integration Login with Dashboard
[Admin_login-2] | Check "Dashboard" Page | 1. Login VMN system by Admin role 2. Click on "Dashboard" hyperlink | 1. Admin Page is displayed 2. "Dashboard" Page is displayed | [Admin module- 20] | Pass | Pass | 22/3/2016
Integration Login with User Management
[Admin_login-4] | Check "User Management" Page | 1. Login VMN system by Admin role 2. Click on "User Management" hyperlink | 1. Admin Page is displayed 2. "User Management" Page is displayed | [Admin module- 27] | Pass | Pass | 22/3/2016
Integration Login with HMS Pending
[Admin_login-6] | Check "HMS Pending" Page | 1. Login VMN system by Admin role 2. Click on "HMS Pending" hyperlink | 1. Admin Page is displayed 2. "HMS Pending" Page is displayed | [Admin module- 35] | Pass | Pass | 22/3/2016
Integration Login with Logout
[Admin_login-8] | When Admin click on "Logout" hyperlink | 1. Login VMN system by Admin role. 2. Click on "Logout" hyperlink on Header | 1. Admin Page is displayed 2. Logout success and redirect to Login Page |  | Pass | Pass | 22/3/2016
Integration User Management with User Detail
[Admin_login-10] | When Admin click on "Detail" button on "User Management" Page | 1. Login VMN system by Admin role 2. Click on "User Management" hyperlink 3. Click on "Detail" button of any user in "User Management" Page | 1. Admin Page is displayed 2. "User Management" Page is displayed 3. "User Detail" Page is displayed | [Admin Module- 29] | Pass | Pass | 22/3/2016
[Admin_login-11] | When Admin click on "Save" button on "User Detail" Page | 1. Login VMN system by Admin role 2. Click on "User Management" hyperlink 3. Click on "Detail" button of any user in "User Management" Page 4. Click on "Save" button on "User Detail" Page | 1. Admin Page is displayed 2. "User Management" Page is displayed 3. "User Detail" Page is displayed 4. "User Management" Page is displayed | [Admin Module- 30] | Pass | Pass | 22/3/2016
[Admin_login-12] | When Admin click on "Lock" button on "User Detail" Page | 1. Login VMN system by Admin role 2. Click on "User Management" hyperlink 3. Click on "Detail" button of any user in "User Management" Page 4. Click on "Lock" button on "User Detail" Page | 1. Admin Page is displayed 2. "User Management" Page is displayed 3. "User Detail" Page is displayed 4. "User Management" Page is displayed | [Admin Module- 33] | Pass | Pass | 22/3/2016
[Admin_login-13] | When Admin click on "UnLock" button on "User Detail" Page | 1. Login VMN system by Admin role 2. Click on "User Management" hyperlink 3. Click on "Detail" button of any user in "User Management" Page 4. Click on "UnLock" button on "User Detail" Page | 1. Admin Page is displayed 2. "User Management" Page is displayed 3. "User Detail" Page is displayed 4. "User Management" Page is displayed | [Admin Module- 32] | Pass | Pass | 22/3/2016
Integration HMS Pending with HMS Detail
[Admin_login-15] | When Admin click on "Detail" button on "HMS Pending" Page | 1. Login VMN system by Admin role 2. Click on "HMS Pending" hyperlink 3. Click on "Detail" button of any user in "HMS Pending" Page | 1. Admin Page is displayed 2. "HMS Pending" Page is displayed 3. "HMS Detail" Page is displayed | [Admin Module- 37] | Pass | Pass | 22/3/2016
[Admin_login-16] | When Admin click on "Accept" button on "HMS Detail" Page | 1. Login VMN system by Admin role 2. Click on "HMS Pending" hyperlink 3. Click on "Detail" button of any user in "HMS Pending" Page 4. Click on "Accept" button on "HMS Detail" Page | 1. Admin Page is displayed 2. "HMS Pending" Page is displayed 3. "HMS Detail" Page is displayed 4. "HMS Pending" Page is displayed | [Admin module- 38] | Pass | Pass | 22/3/2016
[Admin_login-17] | When Admin click on "Deny" button on "HMS Detail" Page | 1. Login VMN system by Admin role 2. Click on "HMS Pending" hyperlink 3. Click on "Detail" button of any user in "HMS Pending" Page 4. Click on "Deny" button on "HMS Detail" Page | 1. Admin Page is displayed 2. "HMS Pending" Page is displayed 3. "HMS Detail" Page is displayed 4. "HMS Pending" Page is displayed | [Admin module- 39] | Pass | Pass | 22/3/2016
Note on F10: Pass Fail Untested N/A
Note on G10: Pass Fail Untested N/A