## Cover
Quality Management System
VMN_Test Report
VMN
Version : 1.0
Document Control information
Issue Date: | 2016-03-31
Issue Status: | Approved
Author: | Trần Bình Khánh
Reviewer information | Hoàng Thị Quỳnh | Test Leader | Required
Approver information | Trần Bình Khánh | Member
Document Revision History
Date | Version | Description | Revised by
2016-03-31 | 1 | Create document | Hoàng Thị Quỳnh
Note on B11: Add more reviewers as necessary
Note on B13: Add more approvers here as necessary

## Report
Test Report
Phase | # Test cases Planned | #Defects Planned | #Test cases Actual | #Defects Actual | % Tests Executed | % Tests Passed | % Tests Fail
Unit Test | 20TC/function | 3 -4 defects/function | 459 |  | 100% | 100% | 0%
Integration Test | 10TC/function | 2 -3 defects/function | 142 | 1 defects/function | 100% | 100% | 0%
System Test | 20TC/function | 4 -6 defects/function | 662 | 9 defects/function | 100% | 100% | 0%
Acceptance Test | N/A | 1-2 defects/function | N/A | 2 defects/function | 100% | 100% | 0%
Total | 50TC/function | 10-15 defects/function | 1263 | 12 defects/function | 100% | 100% | 0%
Phase | Round 1 |  |  |  | Round 2
| Pass | Fail | Untested | N/A | Pass | Fail | Untested | N/A
Unit Test | 459 | 0 | 0 | 0 | 459 | 0 | 0 | 0
Integration Test | 142 | 0 | 0 | 0 | 142 | 0 | 0 | 0
System Test | 470 | 192 | 0 | 0 | 662 | 0 | 0 | 0
Total | 1071 | 192 | 0 | 0 | 1263 | 0 | 0 | 0
Defect report
Defects | Logged | %Closed | %Invalid | %Open
Critical | 0 | 0% | 0% | 0%
High | 3 | 0% | 0% | 0%
Medium | 8 | 100% | 0% | 0%
Low | 5 | 100% | 0% | 0%
Total | 16 | 100% | 0% | 0%